## Red Flag Tracker
PROJECT RIDGELINE — DILIGENCE RED FLAG TRACKER
Ridgeline Environmental Services, Inc. ¦ Prepared for Sycamore Capital Partners, LP ¦ December 2024
RF # | Risk Category | Sub-Category | Description | Severity | Est. Financial Exposure | Source Document(s) | Status | Assigned To | Target Resolution Date | Action Required | SPA Treatment | Notes / Updates | Closed Date
RF-01 | Financial / QoE | EBITDA Quality | Adjusted EBITDA discrepancy: CIM states one figure; QoE data package states a figure approximately $1.0M higher. Gap unreconciled per QoE package itself. | Critical | ~$8–9M valuation impact | CIM §VI.B; QoE EBITDA Bridge tab | Open | Bridgewater Forsyth Group | Pre-signing | Demand fully reconciled EBITDA bridge with line-item support. QoE report must address gap explicitly. | Price protection / true-up mechanism tied to verified Adj. EBITDA
RF-02 | Financial / QoE | Revenue Sustainability | DOE IDIQ ceiling exhaustion: ~73% of ceiling consumed in ~62% of contract period. At current run rate, remaining ceiling exhausted by ~April–May 2025 (target closing date), leaving ~16 months of unfunded contract period. Potential ~$12M revenue headwind in FY2025. | Critical | ~$12M revenue headwind (9–10% of total) | Customer Contract Summary — DOE IDIQ Utilization tab; CIM §VI.D | Open | Deal Team / Seller | Pre-signing | Obtain written confirmation from DOE Contracting Officer re: ceiling modification. Adjust purchase price or structure revenue-based earnout. | Earnout / price adjustment tied to DOE ceiling modification | Not disclosed in CIM investment highlights — buried in supplemental spreadsheet tab
RF-03 | Financial / QoE | EBITDA Quality | Reported EBITDA declined ~27% YoY in FY2024 (TTM). Adjustments represent 24–29% of Reported EBITDA. Several 'non-recurring' adjustment categories recur across multiple years. | High | $4–5M adjustment risk | QoE Historical P&L tab; QoE EBITDA Bridge tab | Open | Bridgewater Forsyth Group | Pre-signing | Require QoE advisor to independently validate each adjustment category and assess recurrence risk. | QoE-adjusted EBITDA as valuation basis | CIM does not present historical Reported EBITDA — trend invisible without QoE data
RF-04 | Financial / QoE | EBITDA Quality | Owner compensation normalization add-back (~$950K) is potentially illusory: founders' salaries are contractually fixed and they are expected to remain post-closing. Achieving the add-back requires renegotiating employment agreements, which triggers single-trigger CoC severance (~$2.6M combined). | High | ~$950K add-back at risk; ~$2.6M severance if renegotiated | QoE EBITDA Bridge tab; Employment Agreements Summary §§3–4 | Open | Deal Team / Legal | Pre-signing | Clarify post-closing compensation arrangements. If founders remain at current salary, eliminate normalization add-back from valuation basis. | Adjust valuation basis; address in employment agreement negotiations | Net economics of normalization are negative if severance is triggered
RF-05 | Financial / QoE | EBITDA Quality | Litigation settlement add-back (~$1.2M) is misidentified in QoE data package. The settlement relates to a previously resolved matter in which the Company received a payment (income), not made a payment (expense). Adding back a one-time income receipt is an unusual and aggressive adjustment. | High | ~$1.2M add-back validity | QoE EBITDA Bridge tab; Litigation & Regulatory Summary §§II.A and IV.A | Open | Bridgewater Forsyth Group | Pre-signing | Require QoE report to clearly identify whether each adjustment is an expense add-back or income exclusion. Confirm source of settlement item. | Potential reduction to Adjusted EBITDA if add-back disallowed | QoE data package mislabels the source of the settlement
RF-06 | Financial / QoE | Capital Expenditures | Fleet deferred capex backlog: ~45% of assets (38 of 85) are at or past stated useful life. Average fleet age of 8.2 years exceeds weighted average useful life of 7.0 years. Estimated replacement cost for past-useful-life units: ~$9.8M. True normalized maintenance capex may be ~$7–8M/yr vs. management's stated $4.0–4.5M/yr. | High | ~$3.3M/yr incremental capex above management estimate | QoE Fleet & Equipment Schedule tab; QoE Capex Detail tab | Open | Deal Team / Operations | Pre-signing | Commission independent fleet condition assessment. Adjust valuation model to reflect true normalized maintenance capex. Negotiate purchase price reduction or escrow holdback. | Capex normalization adjustment to valuation model | Management's capex normalization understates true capital intensity
RF-07 | Financial / QoE | Revenue Concentration | Top 5 customers represent ~50% of TTM revenue; top 10 represent ~67%. Government customers represent ~36% of revenue. 8 of top 20 contracts contain CoC/assignment provisions. 12 of top 20 contracts include termination for convenience with ≤60 days' notice. | Medium | Revenue volatility risk | Customer Contract Summary — Customer Concentration Summary tab | Open | Deal Team / Legal | Pre-signing | Map all CoC notification and consent requirements across top 20 contracts before closing. | Representations re: contract status; consent matrix
RF-08 | Environmental | Phase II ESA / Remediation | Phase II ESA for Grand Junction HQ (only owned property) is 5+ years old (June 2019). Identified petroleum hydrocarbon and chlorinated solvent contamination exceeding regulatory standards. Vapor intrusion assessment explicitly recommended but never conducted. 2019 cost estimate ($1.8–2.6M) excludes vapor intrusion mitigation, off-site remediation, and inflation. Contamination characterized as 'gradual release' — explicitly excluded from PLL policy. | Critical | $2.6M–$5M+ remediation (2024 dollars, excl. vapor intrusion) | Phase II ESA Executive Summary; Environmental Permit Schedule §5; Real Property Lease Schedule §2.1 | Open | Environmental Counsel / Buyer | Pre-signing | Commission updated Phase II ESA and vapor intrusion assessment immediately. Obtain independent remediation cost estimate in current dollars. Negotiate specific environmental escrow with 6-year survival period. Require VCUP enrollment before closing. | Specific environmental indemnification; dedicated escrow; 6-yr survival | No insurance coverage for this liability — gradual release exclusion applies
RF-09 | Environmental | Regulatory Enforcement | CDPHE Notice of Violation (Docket No. CDPHE-HW-2024-0093) issued July 2024 for improper hazardous waste storage at Grand Junction facility. Disputed violation period: Company asserts 12 days (max penalty ~$450K); CDPHE asserts 31 days (max penalty ~$1.16M). No accrual recorded as of fiscal year end. | High | $200K–$1.16M penalty exposure | Litigation & Regulatory Summary §III.A; Environmental Permit Schedule §2.1 | Open | Environmental Counsel / Seller | Pre-closing | Require resolution before closing, or establish specific indemnification escrow of at least $1.2M. Confirm enforcement action will not affect 2026 permit renewal. | Specific indemnification; escrow holdback | Settlement conference expected Q1 2025 — may be after target signing date
RF-10 | Environmental | Permit Transfer | Utah hazardous waste transfer station permit (UTH-0441) for Salt Lake City facility remains in name of acquired subsidiary (Pinnacle Waste Solutions, LLC) despite acquisition closing in March 2022. Transfer application filed but not completed after 2+ years. Proposed acquisition would layer a second CoC event on top of unresolved first transfer. Facility serves ~$16M of annual revenue. | High | ~$16M revenue at risk; potential enforcement action | Environmental Permit Schedule §2.2; Litigation & Regulatory Summary §III.C | Open | Environmental Counsel / Seller | Pre-closing | Obtain written confirmation from Utah Division of Waste Management that current operations are compliant. Make completion of permit transfer a condition of closing. | Permit transfer as closing condition; specific indemnification
RF-11 | Environmental | Permit Renewal | Wyoming hazardous waste permit (WY-HW-2019-033) for Casper facility expired November 30, 2024. Renewal application filed October 15, 2024. Company operating under timely renewal provisions — does not guarantee renewal. Expired permit is also an Event of Default under credit agreement. Casper facility serves ~$30M of Wyoming revenue (~24% of total). | High | ~$30M revenue at risk; potential credit default | Environmental Permit Schedule §2.4; Credit Agreement Summary §10 | Open | Environmental Counsel / Seller | Pre-closing | Obtain written confirmation from Wyoming DEQ of expected renewal timeline. Make permit renewal a condition of closing. | Permit renewal as closing condition; specific indemnification
RF-12 | Environmental | Long-Tail Liability | Asbestos abatement service line operated 2012–2023 at ~145 sites. PLL policy retroactive date of January 1, 2015 leaves 2012–2014 work uninsured. CGL policy has blanket asbestos exclusion with no tail coverage procured. Two workers' comp claims from former asbestos employees remain open. | Medium | Unquantifiable long-tail exposure | Litigation & Regulatory Summary §VI.B; Insurance Program Summary §2; QoE Service Line Detail tab | Open | Legal / Insurance Counsel | Pre-signing | Obtain specific asbestos indemnification from sellers with survival period matching applicable statute of limitations. Evaluate procurement of tail policy covering pre-2015 operations. | Specific asbestos indemnification; extended survival period | ~$31M cumulative asbestos revenue over 11 years — meaningful scale of operations
RF-13 | Debt / Credit | Change of Control | Credit agreement with senior lender contains Change of Control provision triggered by proposed 100% stock acquisition. Upon CoC, Borrower must prepay ALL outstanding Obligations within 5 business days (~$39M total including prepayment premium). No waiver or consent mechanism exists. | Critical | ~$39M mandatory prepayment | Credit Agreement Summary §8; LOI §4.1(b) | Open | Deal Team / Finance | Pre-closing | Confirm acquisition financing includes sufficient proceeds to repay existing credit facility at closing. Obtain payoff letter from lender. | Debt payoff as closing condition; payoff letter required | 5-business-day payoff window creates execution risk
RF-14 | Debt / Credit | Covenant Compliance | Bank's Consolidated EBITDA definition permits only ~$500K of non-recurring add-backs, yielding ~$18.4M vs. management's $22.8–23.8M Adjusted EBITDA. Adjustments expressly excluded under credit agreement definition total ~$4.4–5.4M. Leverage ratio under bank definition is 2.10x (within 3.50x covenant) but headroom could erode rapidly. | High | Covenant compliance risk if EBITDA declines | Credit Agreement Summary §4; QoE EBITDA Bridge tab | Open | Legal / Finance | Pre-signing | Obtain copies of all compliance certificates delivered to lender for past four quarters. Confirm consistency with data room financial statements. | Representation re: covenant compliance; compliance certificate review
RF-15 | Debt / Credit | Key-Man Covenant | Credit agreement requires CEO to remain in role and devote substantially full-time attention to business. His departure without Lender-approved successor constitutes Event of Default with no cure period. Single-trigger CoC severance (~$1.3M) payable at closing regardless of whether he continues — potential misalignment of incentives. | High | Operational/credit risk if CEO departs | Credit Agreement Summary §§7 and 10; Employment Agreements Summary §3 | Open | Legal / Deal Team | Pre-closing | Confirm credit facility will be fully repaid at closing. Negotiate post-closing retention arrangement with CEO separate from CoC severance. | Retention agreement; credit facility payoff at closing
RF-16 | Real Property | Lease Assignment | Salt Lake City transfer station lease (originally executed by acquired subsidiary) has not received landlord consent to assignment despite request filed April 2022 — 32+ months without response. Landlord sent inquiry in November 2024 referencing consent-to-assignment clause. Proposed acquisition would constitute a second CoC event requiring separate consent. Lease has explicit CoC trigger. Facility serves ~$16M of annual revenue. | Critical | ~$16M revenue at risk; potential lease termination | Real Property Lease Schedule §§4.1 and 6; Litigation & Regulatory Summary §V.B | Open | Legal / Seller | Pre-closing (condition of closing) | Obtain written landlord consent to both existing assignment and proposed acquisition as condition of closing. If consent cannot be obtained, identify alternative facility options. | Landlord consent as closing condition; specific indemnification | Landlord's November 2024 inquiry suggests awareness of potential default
RF-17 | Real Property | Lease Expiration | Pueblo, Colorado storage yard lease expires April 30, 2025 — same date as target closing. Renewal negotiations underway but no renewal executed. | Medium | Relocation costs if not renewed | Real Property Lease Schedule §§4.4 and 5 | Open | Operations / Seller | Pre-closing | Require execution of lease renewal or alternative arrangement as condition of closing. | Lease renewal as closing condition
RF-18 | Litigation | Personal Injury | Former field technician filed personal injury lawsuit in August 2024 alleging occupational exposure at Wyoming remediation site. Plaintiff seeks ~$4.8M in damages including punitive damages. Insurer issued reservation of rights letter — coverage not confirmed. Trial scheduled early 2026. No accrual recorded. | High | $500K–$4.8M (coverage uncertain) | Litigation & Regulatory Summary §II.B; Insurance Program Summary §7 | Open | Legal / Insurance Counsel | Pre-signing | Obtain insurer's reservation of rights letter and assess coverage position. Require specific indemnification escrow for this matter. | Specific indemnification escrow; insurance coverage confirmation | Claim exceeds $1M judgment threshold that constitutes Event of Default under credit agreement
RF-19 | Litigation | Labor / NLRB | NLRB election petition filed November 4, 2024 by Teamsters Local 455 covering 62 field technicians at Grand Junction and Casper facilities — Company's two largest operational hubs. Disclosed only in footnote to Employee Benefits Summary; not mentioned in CIM. | High | Labor cost increase; operational disruption risk | Employee Benefits Summary §7 (footnote 1) | Open | Legal / HR | Pre-signing | Obtain full briefing on NLRB petition. Assess likelihood of successful election and potential cost impact. Consider whether petition constitutes Material Adverse Change. | Representation re: NLRB petition; MAC assessment | CIM states workforce is 'entirely non-unionized' — materially undermined by this petition
RF-20 | Litigation | Employment / FLSA | October 2024 demand letter from 8 former field technicians alleging unpaid overtime under FLSA and Colorado COMPS Order. Total claimed exposure ~$330K including liquidated damages. No lawsuit filed. No accrual recorded. | High | $100K–$330K+ (potential collective action) | Litigation & Regulatory Summary §V.A | Open | Legal / HR | Pre-signing | Require specific indemnification for this claim and any related FLSA claims. Obtain employment counsel's assessment of motor carrier exemption defense. | Specific indemnification; FLSA representation | FLSA collective actions can expand significantly if additional employees opt in
RF-21 | Litigation | ERISA / Benefits | Company suspended safe harbor 401(k) employer matching contribution for ~6 months in 2023 due to cash flow management requirements. Mid-year suspension without proper notice may violate IRS safe harbor plan requirements and could result in plan losing safe harbor status for 2023 plan year. | Medium | Up to $500K+ ERISA correction costs | Employee Benefits Summary §4.2 | Open | ERISA Counsel | Pre-signing | Obtain legal opinion from ERISA counsel confirming 2023 safe harbor suspension was properly executed. | ERISA compliance representation; legal opinion | Credit agreement identifies ERISA events >$500K as Event of Default
RF-22 | Gov't Contracts | Anti-Assignment Act | DOE IDIQ contract is non-assignable without prior written consent of Contracting Officer per Anti-Assignment Act (41 U.S.C. § 6305) and FAR 42.12. Contract requires written notification to CO within 30 calendar days of any change in ownership or control; failure to notify is grounds for termination for default. Novation agreement under FAR 42.12 may be required. | Critical | ~$24M revenue at risk (19% of total) | Customer Contract Summary — Top 20 Customers tab and DOE IDIQ Utilization tab | Open | Government Contracts Counsel | Pre-closing | Engage directly with DOE Contracting Officer before closing to determine whether novation agreement is required. Make DOE notification a condition of closing. | Government notification as closing condition; novation agreement if required
RF-23 | Gov't Contracts | Change-of-Control Consents | 8 of top 20 customer contracts contain assignment, CoC, or notification provisions, collectively representing ~$30M+ of annual revenue. Includes DOE, major health system, state environmental agency, pipeline operator, state transportation department, and several commercial customers. | High | ~$30M+ revenue at risk | Customer Contract Summary — Top 20 Customers tab and Customer Concentration Summary tab | Open | Legal / Deal Team | Pre-closing | Develop comprehensive consent and notification matrix for all affected contracts. Prioritize obtaining pre-closing consents from most critical relationships. | Consent matrix; representations re: contract status
RF-24 | Corp. Structure | Change-of-Control Severance | CEO and COO each have single-trigger CoC severance provisions (~$1.3M each, ~$2.6M combined) payable within 30 days of closing regardless of whether employment continues. Total aggregate CoC severance across all 5 executives is ~$3.8M. LOI definition of 'Transaction Expenses' does not explicitly address these payments. | High | ~$2.6M–$3.8M certain closing cost | Employment Agreements Summary §§3–4 and 8; QoE Executive Compensation tab | Open | Legal / Deal Team | Pre-signing | Confirm treatment of CoC severance in SPA (Transaction Expense vs. Buyer cost). Confirm payments do not constitute excess parachute payments under IRC §280G. | SPA treatment of CoC severance; IRC §280G analysis | Single-trigger payments are certain at closing — no employment event required
RF-25 | Corp. Structure | Subsidiary Structure | Acquired subsidiary (Pinnacle Waste Solutions, LLC) is described as dormant since ~Q3 2022, yet remains: (1) permit holder for SLC hazardous waste permit (UTH-0441); (2) named tenant on SLC facility lease; (3) guarantor under credit agreement. Dormant status combined with active legal obligations creates structural complexity. | High | Structural complexity; potential permit/lease loss if dissolved prematurely | Org Chart & Equity Structure §4; Environmental Permit Schedule §2.2; Real Property Lease Schedule §4.1 | Open | Legal / Deal Team | Pre-closing | Do not dissolve subsidiary until all permit transfers and lease assignments are completed. Confirm dormant status does not affect good standing. | Subsidiary preservation covenant; permit/lease transfer as closing conditions
RF-26 | Corp. Structure | Governance | Board of Directors consists of 3 members: CEO (Chairman), COO, and mother of both founders (also Trustee of 35% shareholder trust). No independent directors. Financial statements reviewed (not audited) by local CPA firm. | Medium | Governance risk; potential undisclosed related-party transactions | Org Chart & Equity Structure §5.1; CIM §VI.A | Open | Legal / Deal Team | Pre-signing | Require audited financial statements from nationally recognized accounting firm as condition of closing. Conduct enhanced diligence on related-party transactions. | Audit requirement; related-party transaction representations
RF-27 | Insurance | Coverage Gap | Pollution Legal Liability policy explicitly excludes coverage for gradual contamination at owned or operated facilities. Phase II ESA characterizes Grand Junction contamination as resulting from gradual releases over multiple decades. Company has NO insurance coverage for primary environmental liability at its only owned property. | High | $2.6M–$5M+ uninsured remediation liability | Insurance Program Summary §4; Phase II ESA Executive Summary §4.3 | Open | Insurance Counsel / Legal | Pre-signing | Negotiate specific environmental indemnification from sellers for Grand Junction remediation liability with 6-year survival period. Evaluate procurement of historical contamination endorsement. | Specific environmental indemnification; dedicated escrow; 6-yr survival | Gradual release exclusion is explicit in policy language
RF-28 | Insurance | Claims-Made Tail Risk | Pollution Legal Liability policy is written on claims-made basis with retroactive date of January 1, 2015. At change of control, policy may not automatically transfer to new owner. Tail coverage available at 150% of expiring annual premium for 36-month extension. | High | Uninsured post-closing claims from pre-closing operations | Insurance Program Summary §§4 and 8 | Open | Insurance Counsel | Pre-closing | Confirm with insurer impact of proposed transaction on PLL policy. Procure tail coverage as part of closing process. | Tail coverage procurement; insurance transition plan | Particularly relevant for Ramirez lawsuit (RF-18) and future asbestos claims (RF-12)
RF-29 | IP / Technology | IP Collateral | Both U.S. patents and proprietary software platform are pledged as collateral to senior lender. While debt will be repaid at closing, IP lien must be properly released and UCC financing statements terminated. | Medium | IP encumbrance if lien not properly released | Credit Agreement Summary §3; CIM §X | Open | Legal | At closing | Confirm payoff letter includes commitment to release all IP-related security interests and to file UCC-3 termination statements promptly after closing. | IP lien release as closing deliverable; UCC-3 termination
RF-30 | IP / Technology | ERP Implementation | ERP implementation (Phase 2) is not yet complete as of data room date; expected completion Q2 FY2025. Implementation cost (~$650K) added back as non-recurring item, but implementation is ongoing and may incur additional costs. | Medium | ~$650K+ implementation cost; potential overrun | QoE EBITDA Bridge tab; CIM §X | Open | Operations / Finance | Pre-signing | Obtain detailed project status report and budget-to-actual analysis for ERP implementation. Confirm total expected cost and timeline to completion. | ERP completion representation; cost overrun indemnification
RF-31 | Financial | Financial Reporting | FY2024 (TTM 9/30/24) financials are unaudited. LOI requires delivery of audited financial statements for FY2022, FY2023, and FY2024 as condition of closing. As of data room date, FY2024 audited financials have not been delivered. Financial statements reviewed (not audited) by local CPA firm. | Medium | Financial statement risk; potential material misstatements | CIM §VI.A; QoE Cover & Instructions tab; LOI §8(i) | Open | Bridgewater Forsyth Group / Seller | Pre-signing | Make delivery of FY2024 audited financials (by nationally recognized firm) a condition of signing the SPA, not just closing. | Audit delivery as SPA signing condition | $1.0M EBITDA discrepancy (RF-01) may be symptomatic of inadequate financial controls

## Summary Dashboard
PROJECT RIDGELINE — RED FLAG SUMMARY DASHBOARD
Ridgeline Environmental Services, Inc. ¦ December 2024
SEVERITY SUMMARY
Severity | Count | % of Total | Immediate Action Required
Critical | 6 | 19% | Yes — resolve before signing SPA
High | 14 | 45% | Yes — address in SPA / escrow
Medium | 6 | 19% | Monitor — enhanced reps & warranties
TOTAL | 31 | 100%
RED FLAGS BY RISK CATEGORY
Risk Category | Critical | High | Medium | Total | Key Issues
Financial / QoE | 2 | 4 | 1 | 7 | EBITDA discrepancy; DOE revenue cliff; fleet capex backlog
Environmental | 1 | 3 | 1 | 5 | Stale Phase II ESA; vapor intrusion unassessed; permit issues
Debt / Credit | 1 | 2 | 0 | 3 | Mandatory $39M debt payoff; key-man covenant
Real Property | 1 | 0 | 1 | 2 | SLC lease unresolved assignment; Pueblo lease expiring
Litigation | 0 | 3 | 1 | 4 | Personal injury lawsuit; NLRB petition; FLSA wage claim
Gov't Contracts | 1 | 1 | 0 | 2 | DOE non-assignable; 8 contracts with CoC provisions
Corp. Structure | 0 | 2 | 1 | 3 | Single-trigger severance; dormant subsidiary
Insurance | 0 | 2 | 0 | 2 | Gradual contamination exclusion; claims-made tail risk
IP / Technology | 0 | 0 | 2 | 2 | Patent lien release; ERP Phase 2 incomplete
Financial (Reporting) | 0 | 0 | 1 | 1 | FY2024 financials unaudited
TOTAL | 6 | 14 | 6 | 31
ESTIMATED FINANCIAL EXPOSURE SUMMARY
Exposure Category | Low Estimate | High Estimate | Notes
Mandatory Debt Payoff (RF-13) | $39.2M | $39.3M | Certain at closing; includes prepayment premium
DOE Revenue Headwind FY2025 (RF-02) | $0 | $12.1M | Depends on ceiling modification outcome
Environmental Remediation — GJ (RF-08) | $2.6M | $5.0M+ | 2019 estimate updated for inflation; excludes vapor intrusion
CDPHE Penalty (RF-09) | $200K | $1.16M | Depends on violation period determination
CoC Severance — All Executives (RF-24) | $2.6M | $3.8M | Single-trigger ($2.6M) certain at closing
Personal Injury Lawsuit (RF-18) | $500K | $4.8M | Coverage uncertain; reservation of rights issued
FLSA Wage Claim (RF-20) | $100K | $330K+ | Potential collective action expansion
EBITDA Valuation Impact (RF-01) | $8M | $9M | Based on $1.0M gap at 8.0x–9.0x multiple
Fleet Capex Backlog (RF-06) | $3.3M/yr | $3.3M/yr | Incremental annual capex above management estimate
Asbestos Long-Tail (RF-12) | Unquantifiable | Unquantifiable | Pre-2015 work uninsured; long latency period
TOTAL QUANTIFIABLE EXPOSURE | ~$56M+ | ~$79M+ | Excludes asbestos long-tail and revenue-at-risk items

## Pre-Signing Checklist
PROJECT RIDGELINE — PRE-SIGNING ACTION CHECKLIST
Actions required before signing the definitive Stock Purchase Agreement ¦ December 2024
# | Action Item | Related RF(s) | Priority | Responsible Party | Status | Completion Date
1 | Reconcile the EBITDA discrepancy between the CIM and QoE data package. Obtain fully reconciled EBITDA bridge with line-item support from Bridgewater Forsyth Group. | RF-01 | Critical | Bridgewater Forsyth Group | Open
2 | Obtain written confirmation from DOE Contracting Officer regarding ceiling modification prospects and novation requirements for the IDIQ contract. | RF-02, RF-22 | Critical | Government Contracts Counsel | Open
3 | Commission updated Phase II ESA and vapor intrusion assessment at Grand Junction headquarters. Obtain independent remediation cost estimate in current dollars. | RF-08 | Critical | Environmental Counsel / Buyer | Open
4 | Obtain written landlord consent to both the existing Pinnacle-to-RES assignment and the proposed Sycamore acquisition for the Salt Lake City transfer station lease. | RF-16 | Critical | Legal / Seller | Open
5 | Confirm Utah permit transfer status (UTH-0441) with Utah Division of Waste Management. Obtain written confirmation that current operations are compliant. | RF-10 | Critical | Environmental Counsel / Seller | Open
6 | Obtain FY2024 audited financial statements from a nationally recognized accounting firm. Make delivery a condition of signing the SPA, not just closing. | RF-31 | Critical | Seller / Auditor | Open
7 | Obtain full briefing on NLRB election petition (Teamsters Local 455, 62 employees). Assess likelihood of successful election and potential cost impact. Evaluate MAC implications. | RF-19 | Critical | Legal / HR | Open
8 | Confirm acquisition financing is sufficient to repay the full credit facility (~$39M) at closing. Obtain payoff letter from High Plains National Bank. | RF-13 | Critical | Deal Team / Finance | Open
9 | Clarify post-closing founder compensation arrangements. If founders remain at current salary levels, eliminate the owner compensation normalization add-back from the valuation basis. | RF-04 | High | Deal Team / Legal | Open
10 | Commission independent fleet condition assessment to validate true normalized maintenance capex requirements. | RF-06 | High | Operations / Deal Team | Open
11 | Obtain Wyoming DEQ written confirmation of expected permit renewal timeline for Casper facility (WY-HW-2019-033). Make permit renewal a condition of closing. | RF-11 | High | Environmental Counsel / Seller | Open
12 | Require resolution of CDPHE enforcement action (Docket No. CDPHE-HW-2024-0093) before closing, or establish specific indemnification escrow of at least $1.2M. | RF-09 | High | Environmental Counsel / Legal | Open
13 | Obtain insurer's reservation of rights letter for personal injury lawsuit. Assess coverage position. Require specific indemnification escrow. | RF-18 | High | Insurance Counsel / Legal | Open
14 | Confirm treatment of change-of-control severance (~$3.8M total) in SPA. Conduct IRC §280G analysis for single-trigger payments. | RF-24 | High | Legal / Tax Counsel | Open
15 | Develop comprehensive consent and notification matrix for all 8 contracts with CoC provisions. Prioritize obtaining pre-closing consents. | RF-23 | High | Legal / Deal Team | Open
16 | Obtain ERISA counsel legal opinion confirming 2023 safe harbor 401(k) suspension was properly executed. | RF-21 | Medium | ERISA Counsel | Open
17 | Confirm payoff letter from senior lender includes commitment to release all IP-related security interests and file UCC-3 termination statements. | RF-29 | Medium | Legal | At closing
18 | Obtain ERP implementation project status report and budget-to-actual analysis. Confirm total expected cost and timeline to completion. | RF-30 | Medium | Operations / Finance | Open
19 | Conduct enhanced diligence on related-party transactions given absence of independent board oversight. | RF-26 | Medium | Legal / Deal Team | Open
20 | Confirm with Frontier Specialty Insurance Group the impact of the proposed transaction on the claims-made PLL policy. Procure tail coverage. | RF-28 | Medium | Insurance Counsel | Pre-closing