## Red Flag Tracker
PROJECT RIDGELINE — DUE DILIGENCE RED FLAG TRACKER ¦ Ridgeline Environmental Services, Inc. ¦ December 2024
RF # | Red Flag Title | Category | Severity | Description / Key Finding | Est. Financial Exposure | Source Document(s) | Required Action / Next Step | Owner | Status | Target Date
RF-01 | EBITDA Discrepancy: CIM vs. QoE ($1.0M Gap) | Financial / QoE | HIGH | CIM states Adj. EBITDA = $22.8M; QoE data room shows $23.8M. Management acknowledges the $1.0M gap but has not identified the causative adjustment. The entire $182–205M EV is anchored to this unreconciled metric. | $8–9M valuation impact at 8–9x multiple | CIM (Sec. VI.B); QoE – EBITDA Bridge tab | Require fully reconciled EBITDA bridge signed by CFO and confirmed by Bridgewater Forsyth Group before binding valuation | Buyer / BFG | Open | Pre-Signing
RF-02 | Aggressive EBITDA Add-Backs ($5.4M Aggregate) | Financial / QoE | HIGH | Five add-back categories total $5.4M. Key concerns: (1) $1.2M litigation settlement is a cash receipt, not a cost; (2) ERP Phase 2 ongoing post-closing; (3) Pinnacle integration costs 2.5 yrs post-acquisition; (4) owner comp normalization assumes Calloways remain at market rate. | Up to $5.4M × 8–9x = $43–49M valuation impact | CIM (Sec. VI.B); QoE – EBITDA Bridge; Litigation Summary | Challenge each add-back with BFG; obtain independent confirmation of litigation settlement characterization; require disclosure of post-closing ERP commitments | Buyer / BFG | Open | Pre-Signing
RF-03 | Reported EBITDA Declined 27% YoY in FY2024 | Financial / QoE | MEDIUM-HIGH | Management's Reported EBITDA of $18.4M in FY2024 represents a 27% decline from FY2023's $25.2M, even as revenue grew 11%. This margin compression is obscured by the $5.4M adjustment package and not disclosed in the CIM. | Qualitative; underlying earnings power materially below presented figures | QoE – Historical P&L tab; CIM (Sec. VI.A) | Obtain full FY2023-to-FY2024 reported EBITDA bridge; understand drivers of margin compression | Buyer / BFG | Open | Pre-Signing
RF-04 | Fleet Replacement Backlog — Understated Maintenance Capex | Financial / QoE | MEDIUM-HIGH | 38 of 85 fleet assets (44.7%) are at or past stated useful life. Average fleet age 8.2 yrs vs. 7.0-yr useful life. Deferred replacement cost = $9.8M. Management's normalized maintenance capex of $4.0–4.5M/yr is understated by ~$3.3M/yr of catch-up capex. | $9.8M deferred backlog; ~$3.3M/yr above stated run-rate | QoE – Fleet & Equipment Schedule; QoE – Capex Detail | Commission independent fleet condition assessment; adjust normalized maintenance capex in financial model; negotiate purchase price reduction or escrow holdback | Buyer / Ops Advisor | Open | Pre-Signing
RF-05 | FY2024 Financials Unaudited; Auditor Change Noted | Financial / QoE | MEDIUM | FY2024 financials are reviewed, not audited. CIM references Hansen & Whitfield as accountants; QoE cover references Plante Moran for FY2020–FY2023 — suggesting an auditor change. Auditor transitions can signal accounting disagreements. | Qualitative; data reliability risk | CIM (Sec. VI.A); QoE – Cover & Instructions | Confirm reason for auditor change; require FY2024 audited financials as pre-signing condition (not merely closing condition) | Buyer / Thornfield | Open | Pre-Signing
RF-06 | Grand Junction Phase II ESA Stale (5 Years) — Contamination Scope Understated | Environmental | HIGH | 2019 Phase II ESA identified PCE/TCE and petroleum hydrocarbon contamination. Vapor intrusion risk at maintenance building not assessed. Off-site plume containment unconfirmed. $1.8–2.6M cost estimate excludes vapor intrusion, off-site remediation, and inflation. ESA authors explicitly recommended update prior to any property transaction. No update performed. Gradual-release characterization means PLL insurance is unavailable. | $2.6M+ (likely materially higher with vapor intrusion, off-site, inflation) | Phase II ESA (Elkhorn, June 2019); Environmental Permit Schedule; Insurance Summary (PLL exclusion) | Commission updated Phase II ESA and vapor intrusion assessment immediately; obtain independent remediation cost estimate; negotiate specific environmental escrow with 6-yr survival | Buyer / Env. Counsel | Open | Immediate
RF-07 | CDPHE RCRA Enforcement Action — Active Violation at Grand Junction | Environmental | MEDIUM-HIGH | CDPHE NOV (Docket CDPHE-HW-2024-0093, July 18, 2024) alleges improper storage of 14,000 gal F001/F002 waste. Company position: 12-day violation = $450K max penalty. CDPHE position: 31-day violation = $1.16M max penalty. No accrual recorded. Settlement conference expected Q1 2025. Permit renewal (Dec 2026) could be affected. | $200K–$1.16M penalty; permit renewal risk | Litigation & Regulatory Summary (Sec. III.A); Environmental Permit Schedule | Require resolution prior to closing or negotiate specific indemnification escrow of $1.2M; confirm enforcement action will not affect permit renewal | Buyer / Env. Counsel | Open | Pre-Closing
RF-08 | Wyoming Casper Permit Expired — Operating Under Timely Renewal | Environmental | MEDIUM | WY Permit WY-HW-2019-033 expired November 30, 2024. Renewal application filed October 15, 2024. Company operating under timely renewal provisions. Denial or conditioning of renewal would disrupt Casper operations (68 employees) and trigger credit agreement Event of Default. | Operational disruption; potential Event of Default | Environmental Permit Schedule (Sec. 2.4); Credit Agreement Summary (Sec. 10) | Obtain written confirmation from Wyoming DEQ of renewal timeline; include permit renewal as specific closing condition | Buyer / Env. Counsel | Open | Pre-Closing
RF-09 | Utah SLC Permit Remains in Pinnacle's Name — Transfer Pending Since 2022 | Environmental | MEDIUM-HIGH | Utah Permit UTH-0441 (SLC transfer station) has not been transferred from Pinnacle Waste Solutions, LLC to RES despite the March 2022 acquisition. Company has operated under Pinnacle's permit for ~3 years. Proposed Sycamore acquisition constitutes a further change in operational control requiring new permit modification. | $16.2M revenue at risk from SLC facility disruption | Environmental Permit Schedule (Sec. 2.2); Litigation Summary (Sec. III.C); Org Chart | Require completion of Utah permit transfer as pre-closing condition; obtain written confirmation from Utah DEQ of compliance; assess whether Sycamore acquisition requires separate permit modification | Buyer / Env. Counsel | Open | Pre-Closing
RF-10 | Asbestos Long-Tail Exposure — Pre-2015 Work Not Covered by PLL Policy | Environmental | MEDIUM | RES operated asbestos abatement 2012–2023 (~$31.2M cumulative revenue, ~145 sites). PLL retroactive date is January 1, 2015 — work from 2012–2014 is uninsured. CGL has blanket asbestos exclusion with no tail coverage. Two open WC claims from former asbestos employees. No reserve established. | Unquantified; potentially material for pre-2015 work | Insurance Summary (Sec. 2, 4); Litigation Summary (Sec. VI.B); QoE – Service Line Detail | Quantify pre-2015 asbestos exposure; consider requiring sellers to procure standalone asbestos completed operations tail policy; negotiate specific indemnification carve-out with extended survival | Buyer / Ins. Counsel | Open | Pre-Signing
RF-11 | DOE IDIQ Ceiling Exhaustion — $12.1M+ FY2025 Revenue Headwind | Commercial | HIGH | DOE IDIQ (DE-EM-0005523) = 19.2% of revenue ($24.4M). $32.7M of $45.0M ceiling consumed (72.7%) in 61.7% of contract period. At current run rate, remaining $12.3M ceiling exhausted by April–May 2025. FY2025 DOE revenue could decline to ≤$12.3M — a $12.1M headwind (9.5% of total revenue). Contract also subject to Anti-Assignment Act; novation required for ownership change. | $12.1M+ FY2025 revenue headwind; 9.5% of total revenue | Customer Contract Summary – DOE IDIQ Utilization tab; QoE – Revenue by Customer | Require Company to initiate ceiling increase modification with DOE immediately; obtain CO confirmation on novation; adjust financial model; consider purchase price adjustment tied to DOE revenue performance | Buyer / Gov. Contracts | Open | Immediate
RF-12 | SLC Lease — Unresolved Landlord Consent Creates Default Risk | Commercial | HIGH | SLC transfer station lease (Pinnacle, 2019) defines any change of control as requiring landlord consent. RES requested consent April 12, 2022 — no response in 2.5+ years. Landlord sent compliance inquiry November 2024. Proposed Sycamore acquisition = second CoC event on top of unresolved first. Facility serves ~$16.2M annual revenue. | $16.2M revenue at risk; potential lease termination | Real Property & Lease Schedule (Sec. 4.1); Litigation Summary (Sec. V.B); Customer Contract Summary | Obtain landlord consent to both 2022 Pinnacle assignment and Sycamore acquisition as hard closing condition; engage Wasatch Industrial Properties immediately; assess whether 2.5-yr non-response constitutes pre-existing default | Buyer / Real Estate Counsel | Open | Immediate
RF-13 | 8 Customer Contracts Contain CoC / Assignment Provisions | Commercial | MEDIUM-HIGH | Eight top-20 customer contracts (DOE $24.4M, Intermountain Health $7.1M, Utah DEQ $4.6M, Rocky Mountain Pipeline $4.2M, Bridger Valley $4.1M, Colorado DOT $3.9M, Frontier E&P $2.6M, Teton Steel $2.1M) contain assignment, CoC notification, or consent provisions triggered by the proposed acquisition. | Revenue at risk across multiple relationships; aggregate ~$51M | Customer Contract Summary – Top 20 Customers tab; Customer Concentration Summary tab | Conduct systematic consent solicitation for all 8 contracts; prioritize DOE novation and Intermountain Health consent; build consent receipt into closing conditions | Buyer / Thornfield | Open | Pre-Closing
RF-14 | CMMC MSA — 60-Day Termination for Convenience; No Minimum Volumes | Commercial | MEDIUM | Consolidated Mining & Minerals Corp. (11.4% of revenue, $14.5M) governed by MSA with annual auto-renewal and 60-day termination for convenience by either party. No minimum volume commitments. CIM characterizes as 'long-standing' without disclosing termination risk. | $14.5M revenue at risk with 60-day notice | Customer Contract Summary – Top 20 Customers tab; CIM (Sec. VI.D) | Seek multi-year contract extension with CMMC prior to closing; assess CMMC financial condition and competitive threats | Buyer / BD Team | Open | Pre-Closing
RF-15 | Customer List Discrepancy Between CIM and QoE Data Room | Commercial | MEDIUM | CIM/contract summary and QoE Revenue by Customer tab present materially different customer names at the same revenue ranks (e.g., 'Western Slope Municipal Water District' vs. 'Western Slope Energy Partners'; 'Intermountain Health' vs. 'Suncor Energy'). Aggregate revenue reconciles but customer-level attribution does not. | Qualitative; data integrity and consent process risk | CIM (Sec. VI.D); Customer Contract Summary; QoE – Revenue by Customer | Require single reconciled customer revenue schedule signed by CFO; confirm which names/figures are accurate for contract consent process | Buyer / BFG | Open | Pre-Signing
RF-16 | Mandatory Credit Facility Prepayment — $38.7M Due Within 5 Business Days | Debt / Capital | HIGH | Senior secured credit agreement (High Plains National Bank) triggers mandatory full prepayment within 5 business days of a Change of Control. Total funded debt = $38.7M ($12.4M revolver + $26.3M term loan). Term loan carries 1.0% prepayment premium (~$263K). No waiver or consent mechanism exists in the credit agreement. | $38.96M+ (principal + $263K premium + accrued interest) | Credit Agreement Summary (Sec. 8, 9); CIM (Sec. XII.B); LOI (Sec. 4(b)) | Arrange acquisition financing and payoff letter with HPNB well in advance of closing; confirm prepayment premium calculation; include premium and accrued interest in Net Debt definition in SPA | Buyer / Finance | Open | Pre-Signing
RF-17 | Bank EBITDA vs. Management EBITDA — 2.10x vs. 1.70x Leverage Gap | Debt / Capital | MEDIUM | Bank Consolidated EBITDA definition excludes all 5 management add-back categories. Bank EBITDA ≈ $18.4M → leverage = 2.10x (not 1.70x as implied by management). Buyer's acquisition lenders will likely use a similar definition, affecting financing terms and available leverage. | Financing terms impact; potential leverage constraint | Credit Agreement Summary (Sec. 4); QoE – EBITDA Bridge | Model acquisition financing using bank-definition EBITDA; confirm covenant compliance through closing date | Buyer / Finance | Open | Pre-Signing
RF-18 | Derek Calloway Key-Man Provision in Credit Agreement | Debt / Capital | MEDIUM | Credit agreement treats Derek Calloway's departure as CEO without Lender-approved successor as an Event of Default. Provision extinguished at payoff, but underscores key-man dependency — particularly for DOE contracting relationship. Single-trigger CoC severance does not require Calloway to remain post-closing. | Qualitative; operational and relationship continuity risk | Credit Agreement Summary (Sec. 7); Employment Agreements Summary (Sec. 3) | Negotiate robust post-closing retention arrangements with Derek Calloway; consider earnout or equity rollover to align incentives | Buyer / HR / Thornfield | Open | Pre-Signing
RF-19 | Pueblo Storage Yard Lease Expires at Closing — No Renewal Secured | Real Property | LOW-MEDIUM | Pueblo Storage Yard lease (2280 Santa Fe Ave, Pueblo, CO) expires April 30, 2025 — same month as target closing. Renewal negotiations 'underway' but no terms agreed. Facility used for equipment and vehicle storage. | Relocation costs; minor operational disruption | Real Property & Lease Schedule (Sec. 3, 4.4) | Require lease renewal as pre-closing deliverable or confirm alternative storage arrangements | Buyer / Ops | Open | Pre-Closing
RF-20 | Grand Junction Property Appraisal Stale (3 Years); Environmental Impairment | Real Property | LOW-MEDIUM | Grand Junction owned property appraised at $6.8M in March 2022. No updated appraisal commissioned. Environmental contamination disclosed in Phase II ESA may materially impair market value. Property serves as collateral for HPNB credit facility. | Collateral value uncertainty; potential impairment | Real Property & Lease Schedule (Sec. 2.1); Phase II ESA; Credit Agreement Summary (Sec. 3) | Commission updated appraisal incorporating environmental conditions; assess whether contamination materially impairs collateral value for acquisition financing | Buyer / Finance / Env. Counsel | Open | Pre-Signing
RF-21 | NLRB Unionization Petition — 62 Field Technicians at Core Facilities | Human Capital | MEDIUM-HIGH | Teamsters Local 455 filed NLRB election petition November 4, 2024 covering 62 field technicians at Grand Junction and Casper — the Company's two largest operational hubs. Not disclosed in CIM. Successful election could result in collective bargaining, wage increases, work rule changes. Credit agreement treats material labor dispute >10 business days as Event of Default. | Labor cost increases; operational disruption; potential Event of Default | Employee Benefits Summary (Sec. 7, fn. 1); CIM (Sec. VII.A) | Obtain full briefing on NLRB petition status and Company response strategy; assess likelihood of successful election; model financial impact of collective bargaining; assess whether petition constitutes MAC under LOI | Buyer / Labor Counsel | Open | Immediate
RF-22 | Single-Trigger CoC Severance — $2.625M Certain Cash Outflow at Closing | Human Capital | MEDIUM-HIGH | CEO Derek Calloway and COO Jason Calloway have single-trigger CoC severance of $1,312,500 each ($2,625,000 combined), payable within 30 days of closing regardless of post-closing employment. Double-trigger provisions for Engel ($425K), Dillon ($375K), Oakes ($350K) total $1,150,000 contingent. LOI does not expressly address treatment of CoC severance in Transaction Expenses definition. | $2.625M certain at closing; $1.15M contingent | Employment Agreements Summary (Sec. 2, 8); QoE – Executive Compensation tab; LOI (Sec. 4(c)) | Confirm treatment of CoC severance in SPA Transaction Expenses definition; negotiate post-closing employment arrangements with Calloways; consider renegotiating single-trigger to double-trigger in exchange for enhanced retention | Buyer / Thornfield / HR | Open | Pre-Signing

## Summary Dashboard
PROJECT RIDGELINE — RED FLAG SUMMARY DASHBOARD
Ridgeline Environmental Services, Inc. ¦ Proposed Acquisition by Sycamore Capital Partners, LP ¦ December 2024
TOTAL RED FLAGS 22 |  | HIGH SEVERITY 6 |  | MEDIUM-HIGH 8 |  | MEDIUM / LOW-MEDIUM 8
Category | # Red Flags | HIGH | MEDIUM-HIGH | MEDIUM | LOW-MEDIUM | Max Exposure (Indicative)
Financial / QoE | 5 | 2 | 1 | 1 | 0 | Up to $49M+ valuation impact
Environmental | 5 | 1 | 2 | 2 | 0 | $5M+ (remediation, penalties, tail)
Commercial Contracts | 5 | 2 | 1 | 2 | 0 | $12.1M revenue headwind + $16.2M lease risk
Debt / Capital | 3 | 1 | 0 | 2 | 0 | $38.96M mandatory prepayment
Real Property | 2 | 0 | 0 | 0 | 2 | Collateral impairment; relocation costs
Human Capital | 2 | 0 | 2 | 0 | 0 | $2.625M certain + $1.15M contingent
TOTAL | 22 | 6 | 6 | 7 | 2 | See Red Flag Tracker for detail
SEVERITY LEGEND
HIGH: Requires immediate attention; potential deal-breaker or material price adjustment |  | MEDIUM-HIGH: Significant risk; requires resolution before closing or specific indemnification |  | MEDIUM: Moderate risk; requires diligence follow-up and SPA protection |  | LOW-MEDIUM: Lower risk; monitor and address in ordinary course
KEY FINANCIAL METRICS — AS PRESENTED vs. DILIGENCE-ADJUSTED
Metric | CIM / Management | QoE / Bank Definition | Diligence Concern
FY2024 Adjusted EBITDA | $22.8M (CIM) / $23.8M (QoE) | $18.4M (bank definition) | RF-01, RF-02: $1.0M unexplained gap; $5.4M add-backs excluded by bank
Implied EV / EBITDA | 8.0x–9.0x on $22.8M Adj. EBITDA | 9.9x–11.1x on $18.4M bank EBITDA | RF-01, RF-02: Multiple materially higher on clean earnings
Total Leverage | 1.70x (mgmt. EBITDA) | 2.10x (bank EBITDA) | RF-17: Financing terms based on bank definition
Normalized Maint. Capex | $4.0–4.5M/yr (management) | ~$7.3–7.8M/yr (incl. fleet backlog) | RF-04: $9.8M deferred fleet replacement; ~$3.3M/yr catch-up
DOE Revenue (FY2025E) | $24.4M (TTM run rate) | ≤$12.3M (ceiling exhaustion) | RF-11: $12.1M+ revenue headwind if ceiling not increased
Mandatory Debt Payoff | $38.7M principal | $38.96M+ (incl. premium + interest) | RF-16: 5-business-day prepayment window; no waiver mechanism
CoC Severance (Certain) | Not in CIM | $2.625M (single-trigger, at closing) | RF-22: Calloway brothers; payable regardless of employment
Environmental Accrual | $3.2M (all facilities) | $3.2M+ (likely understated) | RF-06: 2019 ESA stale; vapor intrusion and off-site not included

## Action Item Register
PROJECT RIDGELINE — ACTION ITEM REGISTER
RF # | Action Required | Priority | Target Timing | Owner | Status | Notes
RF-01/02 | Demand fully reconciled EBITDA bridge; resolve $1.0M discrepancy; validate all add-backs with BFG | CRITICAL | Pre-Signing | Buyer / BFG | Open | Blocking item for binding valuation
RF-06 | Commission updated Phase II ESA and vapor intrusion assessment at Grand Junction | CRITICAL | Immediate | Buyer / Env. Counsel | Open | ESA authors explicitly recommended update prior to any transaction
RF-11 | Initiate DOE ceiling increase modification request; obtain CO novation guidance | CRITICAL | Immediate | Buyer / Gov. Contracts | Open | Long-lead-time item; ceiling exhaustion projected April–May 2025
RF-12 | Engage Wasatch Industrial Properties for SLC lease consent (2022 assignment + Sycamore acquisition) | CRITICAL | Immediate | Buyer / Real Estate Counsel | Open | Hard closing condition; $16.2M revenue at risk
RF-16 | Arrange acquisition financing; obtain HPNB payoff letter; confirm prepayment premium | CRITICAL | Pre-Signing | Buyer / Finance | Open | 5-business-day mandatory prepayment window at closing
RF-21 | Obtain full briefing on NLRB Teamsters petition; assess MAC implications | CRITICAL | Immediate | Buyer / Labor Counsel | Open | Not disclosed in CIM; covers 62 employees at core facilities
RF-04 | Commission independent fleet condition assessment; adjust normalized maintenance capex | HIGH | Pre-Signing | Buyer / Ops Advisor | Open | $9.8M deferred replacement backlog; ~$3.3M/yr above stated run-rate
RF-05 | Confirm auditor change rationale; require FY2024 audited financials pre-signing | HIGH | Pre-Signing | Buyer / Thornfield | Open | LOI requires audited financials as closing condition; should be pre-signing
RF-07 | Require CDPHE enforcement resolution pre-closing or negotiate $1.2M specific escrow | HIGH | Pre-Closing | Buyer / Env. Counsel | Open | Settlement conference expected Q1 2025
RF-08 | Obtain Wyoming DEQ written confirmation of renewal timeline; add as closing condition | HIGH | Pre-Closing | Buyer / Env. Counsel | Open | Permit expired November 30, 2024
RF-09 | Require Utah permit transfer completion as pre-closing condition | HIGH | Pre-Closing | Buyer / Env. Counsel | Open | Pending since March 2022 acquisition
RF-13 | Conduct systematic consent solicitation for all 8 contracts with CoC provisions | HIGH | Pre-Closing | Buyer / Thornfield | Open | Prioritize DOE novation and Intermountain Health
RF-22 | Confirm CoC severance treatment in SPA; negotiate Calloway post-closing retention | HIGH | Pre-Signing | Buyer / Thornfield / HR | Open | $2.625M certain at closing; single-trigger structure
RF-10 | Quantify pre-2015 asbestos exposure; consider requiring sellers to procure tail policy | MEDIUM | Pre-Signing | Buyer / Ins. Counsel | Open | 2012–2014 work not covered by current PLL retroactive date
RF-14 | Seek multi-year CMMC contract extension prior to closing | MEDIUM | Pre-Closing | Buyer / BD Team | Open | $14.5M revenue; 60-day termination for convenience
RF-15 | Require reconciled customer revenue schedule signed by CFO | MEDIUM | Pre-Signing | Buyer / BFG | Open | Customer names differ between CIM and QoE data room
RF-17 | Model acquisition financing using bank-definition EBITDA | MEDIUM | Pre-Signing | Buyer / Finance | Open | 2.10x leverage on bank EBITDA vs. 1.70x on management EBITDA
RF-18 | Negotiate post-closing retention for Derek Calloway; consider earnout/equity rollover | MEDIUM | Pre-Signing | Buyer / HR / Thornfield | Open | Key-man risk for DOE relationship and operations
RF-19 | Require Pueblo lease renewal as pre-closing deliverable | LOW | Pre-Closing | Buyer / Ops | Open | Lease expires April 30, 2025 — same month as target closing
RF-20 | Commission updated Grand Junction property appraisal incorporating environmental conditions | LOW | Pre-Signing | Buyer / Finance / Env. Counsel | Open | 2022 appraisal stale; contamination may impair collateral value